## Sprint Backlog(Scrum - AMS)
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | US-1 | 1 | Admin /Customer is logged in | Sashank Nanduri | 2020-06-07 | 10 hrs | 3 hrs |  | 13 hrs
|  | 2 | Admin/Customer can accesss System | Sashank Nanduri
|  | 3 | Customer can Update Details | Sashank Nanduri
2 | US-2 | 1 | Customer can Book Hotel | Siddharth Wagadre | 2020-06-07 | 10 hrs | 4 hrs |  | 14 hrs
|  | 2 | Customer can Delete Booking | Siddharth Wagadre
|  | 3 | Customer can check the status of Booking | Siddharth Wagadre
|  | 4 | Customer can get Booking by name and id | Siddharth Wagadre | 2020-06-07 | 10 hrs | 4 hrs |  | 14 hrs
3 | US-3 | 1 | Admin can add new Hotel to database | Avinash Londhe | 2020-06-07 | 6 hrs | 3 |  | 6 hrs
|  | 2 | Admin can update the Hotel database | Avinash Londhe
|  | 3 | Admin can get all the Hotels Details | Avinash Londhe | 2020-06-07 | 10hr | 1hr |  | 11hr
|  | 4 | Admin can delete all the hotel details | Avinash Londhe
6 | US-4 | 1 | Admin can add room to the database | Nikhil Kale
|  | 2 | Admin can delete the room | Nikhil Kale | 2020-06-07 | 5hr | 0hr |  | 5hr
|  | 3 | Admin can Update room in the database | Nikhil Kale
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.

## General Instructions
#REF! |  |  |  |  | #REF!
2020-06-14 15:23
General Instructions
1 | Use this template to create a MoSCoW (Must have, Should Have, Could Have, or Won't Have) Requirements Work Product.
2 | Also consider using this template as a traceability matrix. Additional Sheets have been provided after the MoSCoW sheet that will facilitate the traceability of high level requirements to functional requirements, to business rules, to Service Oriented Architecture, to Test Cases, as appropriate for individual projects.
3 | This work product is meant to scale up or down; under some conditions, you may want to merge work products from other tasks into this one as additional sheets. In some situations, the project may be very large, in that case, it is recommended that an automated tool is used such as Oracle Enterprise Repository, rather than using this spreadsheet to produce your work product.
4 | Each individual worksheet contains instructions on how it should be used. See cells with comments as indicated by the red triangle in the upper right corner of the cell.
|  | Condition | Approach
|  | COTS Functionality | For Commercial Off the Shelf Software requirements stated in the Statement of Work or in the Project Charter, add a line to the Original Requirements sheet and to the MoSCoW list. If you are using the MoSCoW as a traceability matrix, you will need to tie the test case that authenticates the requirement to the requirement on the MoSCoW list.
|  | Requirements on MoSCoW tab without Use Case ID's | Requirements should tie to another form of implementation that satisfies the requirement. Some examples are COTS, Business Rules, Service, Non-functional Requirement.
|  | Use Case Catalog | When there are more than 20 use cases consider breaking up this catalog into multiple sheets by package groups (i.e. Data Access, Architecture, Data Acquisition), or by Actor (Procurement Manager, Buyer, Accounts Payable Specialist).
|  | New requirements may be added to the Original Requirements sheet | When Requirements are added to the Original Requirements sheet they should have a Source other than the Statement of Work(i.e. Meeting Minutes, CR, etc. with the corresponding dates).
|  | Business Rules or calculations may be managed within the application, or enterprise repository | Review the task RA.027 Identify Candidate Business Rules to understand how rules may be identified from use cases. Consider entering candidate Business Rules specified in the SOW or in subsequent work sessions into the RA.027, but manage rules/calculations within the application or tool. You may choose to combine the spreadsheet from the RA.027 into this workbook for smaller projects.
|  | SOA Services may be managed within a middleware tool or within the enterprise repository | You should review the task RA.025 Identify Candidate Services. You may choose to combine the spreadsheet from the RA.025 into this workbook for smaller projects.
|  | Scrum Product backlog and Sprint Backlog are included in this workbook | Project Managers using a Scrum approach to project management will use the last two sheets of this workbook for the Product Backlog and Sprint Backlog. Please review the Using Scrum in OUM White paper prior to using these sheets.

## Sheet Definitions
Worksheet | Purpose
Original Requirements | This worksheet identifies the original requirements gathered from the contract, the statement of work (SOW), and the Proof of Concept (POC) and any other relevant collateral provided from project definition.
RD.045.Moscow List | This worksheet categorizes and prioritizes the requirements. At a minimum, this sheet should hold requirements as defined in the statement of work or project charter. At the start of the project, the requirements listed in the "Original Requirements" and the "RD.045 MoSCoW List" tab would normally be the same, or at least, there should be a 100% coverage between the two.
RA.023 Use Case Catalog | List all the Use Cases for the project from the RA.023 Use Case Model, and cross reference back to the MoSCoW sheet for the requirement that the use case satisfies.
RD.055 Supplementary Req | Use this sheet to record the Supplemental Requirements for the project. See the task guideline for the Task RD.055 Detail Supplemental Requirements
RA.025 Services Traceability | Use this sheet to capture traceability back to the Services that are documented in the work product for Task RA.025 Identify Candidate Services.
RA.027 Rules Traceability | Use this sheet to capture traceability to Business rules that are documented in the work product for Task RA.027 Identify Candidate Business Rules. For small projects you may choose to combine work products and insert the RA.027 work product here.
TE.0xx Test Traceability | This worksheet tracks test cases as outlined in the Test Plan. This worksheet can be used to populate the Test results work product(s) if a formal document is required.
RD.042 Glossary Traceability | Project Glossary used for traceability across multiple work products. Common terms used in this spreadsheet should be documented here to ensure terms used in the requirements are understood by both technical and business project members. If the term changes, impact analysis can be done to determine which artifacts would require the term change.

## RA.023 Use Case Catalog
MoSCoW ID | Use Case ID | Use Case Name (verb/noun) | Actors | Iteration Group | Customer Priority | Risk/ Impact | Complexity | Use Case Dependency | Source | Date | Package | Comment | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | UC.01 | Read/Update/Add/delete Booking | Customer |  | Must
2 | UC.02 | View hotels details | Admin |  | Must
3 | UC.03 | Login/logout | Admin,Customer |  | Must
4 | UC.04 | Read/Update/Add/delete hotel | Admin |  | Must
5 | UC.05 | Add/Update/read/Delete room | Admin |  | Must
6 | UC.06 | Check status | Admin/Customer |  | Must
This worksheet is intended to be used to capture a catalog of the Use Cases, this list is taken from the RA.023 Use Case Model.

## TE.0xx Test Tracability
This worksheet is intended to be used to document test scenarios and test results based on the Test Plans.
This sheet could be duplicated once for each type of test if the number of tests in the sheet becomes too large
MoSCoW ID | Test Scenario ID | Test Type | Test Scenario Name | Result (Pass or Fail) | Tester | Comments
| U001 | Unit
| INT010 | Integration
| SYS101 | System
| SYSINT010 | Systems Integration
| UAT010 | Acceptance
Test results may be recorded and traced back to requirements on the MoSCoW as a result of the following:
TE.030 Unit Test
TE.040 Integration Test Results
TE.070 System Test Results
TE.100 Systems Integration Test Results
TE.120 Acceptance Test Results

## Sprint Backlog (Scrum)-AMS
Product Backlog ID | User Story ID | User Story Task Step number | Task Step description | Assigned to | Assigned Date | Original Estimate | Adjusted estimate | Status | Actual Effort | Comment | Columns to the right are OPTIONAL depending on the level of rigor applied to the project. | Module or Component ID | Unit Test Scenario ID | System Test Scenario ID | Systems Integration Test Scenario ID
1 | US-1 | 1 | Admin /Customer is logged in | Sashank Nanduri | 2020-06-07
|  | 2 | Admin/Customer can accesss System | Sashank Nanduri
|  | 3 | Customer can Update Details | Sashank Nanduri
2 | US-2 | 1 | Customer can Book Hotel | Siddharth Wagadre | 2020-06-07
|  | 2 | Customer can Delete Booking | Siddharth Wagadre
|  | 3 | Customer can check the status of Booking | Siddharth Wagadre
|  | 4 | Customer can get Booking by name and id | Siddharth Wagadre | 2020-06-07
3 | US-3 | 1 | Admin can add new Hotel to database | Avinash Londhe | 2020-06-07
|  | 2 | Admin can update the Hotel database | Avinash Londhe
|  | 3 | Admin can get all the Hotels Details | Avinash Londhe | 2020-06-07
|  | 4 | Admin can delete all the hotel details | Avinash Londhe
6 | US-4 | 1 | Admin can add room to the database | Nikhil Kale
|  | 2 | Admin can delete the room | Nikhil Kale | 2020-06-07
|  | 3 | Admin can Update room in the database | Nikhil Kale
List User Story steps that were not completed at Sprint End
When using a Scrum approach to project management, this worksheet is intended to capture the detail tasks of User Stories for the current Sprint.
Note, this is further detail of the user stories that appear on the Product Backlog sheet.